TECHNICAL REVIEW REPORT

Grant Agreement number: 621040

Project Acronym: i-locate

Pilot A □   Pilot B X   Thematic Network □   Best Practice Network □ PPI Pilot□

Project start date: 1.1.2014

Project duration: 36 months

Period covered by the report, from 1.1.2014 to 31.12.2014

Date of review meeting: 5.2.2015

Name(s) of expert(s):

- Aleksander Buczkowski

- Kevin Curran

Individual report	□

Consolidated report	 X

If consolidated, name of expert drafting the consolidated report: Kevin Curran

1. 	OVERALL ASSESSMENT

a.	Executive summary

Comments, in particular highlighting the project progress towards achieving its objectives and reaching its impact:

The project to date has met the targets outlined in the work plan for the first period under review. The project objectives remain relevant and the resources planned and utilised in relation to the achieved progress are still applicable. The management of the project is satisfactory and the methods of the project to date are appropriate. The contributions of the partners are in line with those targets, tasks and time-lines originally devised. The expected potential impact and the appropriateness of the planned use and dissemination of results are as expected. There is an excellent potential impact for i-locate as the location based services field rapidly expands. Overall, excellent progress has been achieved. Most the materials provided are comprehensive, well written and the logical structure of all the deliverables is adequate. The project has a potential to introduce a real innovation within the indoor location-based services industry. The consortium actively cooperates with the key industry stakeholders including leading technology and standardization bodies. There are minor recommendations.

X        Excellent progress (the project has fully achieved its objectives and goals for the period and has even exceeded expectations).

         Good progress (the project has achieved most of its objectives and goals for the period with relatively minor deviations).

- Acceptable progress (the project has achieved some of its objectives; however, corrective action will be required).

- Unsatisfactory progress (the project has failed to achieve critical objectives and/or is not at all on schedule).

b.	Overall recommendations (e.g. corrective actions at Work Package level, or re-tuning the objectives to optimise the impact or keep up with the developments in relevant policies, or on best use of resources).

WP2/WP6:

- The comprehensive analysis of regulatory constrains have been performed for both European and member state (countries of pilot sites) levels. The consortium identified regulatory barriers including: lack of defining indoor spaces as geographic information, lack of defining public spaces and publicly available spaces in the context of open geographic data, and lack of indoor data sharing regulations among others. Using the know-how of the consortium it would be recommended that the consortium contribute to solving this issues by recommending particular solutions in that matter. Such a regulatory recommendations will strengthen the position of the consortium in discussions with public and private institutions, as well as the industry leader.

WP6:

- Comprehensive and active dissemination actions of the consortium are focussing mostly on building awareness of the technology and the platform build by the consortium. In parallel, possibly allocating unused resources from WP6, the activities could be extended to more actively promote openness of indoor spatial data (building plans) among all the stakeholders outside of the end users of the technologies. The lack of the data of indoor spaces have been identified by the consortium as a key barrier and a key success factor not only for the project itself but for the whole industry.

WP1/WP2/WP4:

- Large number of pilots will allow testing and fine-tuning tools developed during the period of the project. The consortium will use different technologies for similar use-case scenarios during the pilot phase. Moreover the consortium stated that it will test additional technologies provided by interested in the project third party technology providers. It would be beneficial for the industry and researchers if they could publish the assessment of different technologies used in different scenarios, comparison of the technologies and the best practises. This would bring additional added value to the industry and strengthen the position of the consortium as the industry leader.

2. 	OBJECTIVES, QUALITY and PROGRESS OF WORK

a.	Have the objectives for the period been achieved?  In particular, has the project as a whole been making satisfactory progress in relation to the Description of Work (Annex I to the grant agreement)?

Comments – in particular highlight any outstanding achievements

Overall the project seems on course to 1) deploy a public portal for access to open mapping data 2) build a final version of the toolkit which is tested in different pilot sites 3) release a number of mobile applications addressing various use cases; 4) define business models based on indoor and outdoor LBS and 5) define contractual arrangements and Service Level Agreements (SLA) for i-locate services. The project has made excellent progress. All objectives, deliverables and milestones for the period of the project had been achieved.

b.	Has each work package (WP) been making satisfactory progress in relation to the Description of Work (Annex I to the grant agreement)?

Comments on the quality of work per work package

All milestones have been achieved. WP1 has identified all the preparatory aspects of the pilots ranging from the definition of the use cases and user requirements, to regulatory issues, to privacy and security requirements, up to the definition of the system architecture of the i-locate framework, including the portal, middleware, and client applications. This WP required the involvement of virtually all the partners. WP2 are proceeding according to plan and in some cases are ahead of schedule e.g. deployment of the first public version of the “virtual hub” (the geoportal). WP3 has seen the release of the first version of the i-locate toolkit. This first version of the i-locate toolkit, whose source code has been officially released to the public domain4, already supports a number of RTLS including ZigPos, Quuppa, and Wi-Fi indoor localization. WP4 has seen the pilots deployment and validation plan released in M10. The main contents of this deliverable included, for each pilot site, a detailed deployment procedures of the various RTLS, the validation guidelines for each RTLS technology, the roll-out agenda. Other supported planned work has taken place in other tasks. WP5 has no activity to report within this reporting period since, according to the work plan, the activities of this WP are scheduled to start later during the second reporting period. WP6 describes how the partners have focused on raising awareness about the project among the general public and within relevant communities of potential customers (e.g. cities, hospitals, public bodies and large organisations, retailers, etc.), data providers, and technical developers. Liaisons have been established with several stakeholders targeted and specific objectives for year 1 are outlined. Finally, WP7 activities include the appointment of the management structure, editing and checking of internal bi-monthly reports, book-keeping activities, preparation of project meeting, coordination of the project and steering of high-level awareness strategy of the project.

c. 	Have planned milestones and deliverables been achieved for the reporting period?

Overall comments with a focus on milestones – detailed comments per deliverable are annexed to this review report (if evidence of plagiarism is identified it should be mentioned here and described in more detail in the annexed deliverable table)

Within this first reporting period there has not been any major significant deviations from the effort planned in any of the work packages. The resources overall have been a little over. This should not cause any significant problems in budgeting for the next period. With regards milestones: MS1- Conclusion of analysis phase, MS2 - Release of the first version of the i-locate toolkit and MS3- Release of first training framework have all been delivered.

d.	Are the objectives for the coming period(s) i) still relevant and ii) still achievable within the time and resources available to the project? Note that both aspects (i) and (ii) have to be covered in the comments.

Comments

ad (i) The objectives are still relevant. Objectives 1, 2, and 3 related to the development of the i-locate portal, middleware, and client software, have been fully met with the first release of the technology. The objectives relating to (4) The definition of specific privacy and security policies. (5) The extension of current location based standards to properly cater for requirement of hybrid indoor and outdoor tracking and routing scenarios. (6) pilots (7) dissemination of the results and (8) ensuring commercial exploitation of the project - all remain relevant. ad (ii) The objects are still achievable within the time and resources available to the project.

3.	RESOURCES and IMPLEMENTATION OF THE PROJECT

a.	To the best of your estimate, have resources used, i.e. personnel resources and other major cost items, been (i)  utilised for achieving the progress, (ii)  in a manner consistent with the principle of economy, efficiency and effectiveness. Note that both aspects (i) and (ii) have to be covered in the comments.  The resources should be examined at the level of work packages and at the level of participants.

Comments

ad (i) The resources used and other major cost items have been utilised for achieving the progress of the project. We cannot see any trips or items which have been outlined which are not reasonable items of expenditure. Minor deviations to the costs have been observed. The consortium explained all the deviations during the review meeting. All the comments will be included in the final report submitted by the consortium. ad (ii) The resources used have been in a manner consistent with the principle of economy, efficiency and effectiveness for this project.

b.	If applicable, please comment on large deviations with respect to the planned resources.

Comments

The partners have been upfront about the major landslide which caused the administration to request a change in their pilot area. However, since this change occurred during the preparation phase, the change could be accommodated with absolutely no impact on the project activities. The Galileo service is not fully operational but this is beyond the control of the consortium and also does not represent a blocking factor for piloting activities, as GPS support is already included in v.1.0 of the toolkit and EGNOS support will be added by M18. No impact on resources is foreseen. There have been no other notable large deviations from the planned resources.

c.	Do you identify evidence of underperforming beneficiaries, lack of commitment/performance or change of interest of any beneficiaries?  Do you identify any beneficiaries with no visible contribution to the project in the examined period?

Comments

None. The document does however comment on the late joining of Comune di Tremosine sul Garda, together with the change of administration which caused lower engagement by the partner at the start. However as a remedial action, the PC called a meeting several times with the new mayor and the other management staff so as to engage them within the project activities. The new administration is now fully committed within the project.

4.	MANAGEMENT and COLLABORATION

a.	Has the project management been performed as required?

Comments

The project management has been performed satisfactorily. The project is coordinated by Trilogis led by (PC), Dr Giuseppe Conti. He is also supported by an Administrative Assistant (AA, Ms. Irene Facchin), the Quality and Risk Manager (QRM, Mr. Gianni Rangoni), and the Technical Manager (TM, Mr. Stefano Piffer), all from Trilogis. The project uses PMI Project Management Methodology for the overall management as well as Agile methodology for the software development. The project manager proven to be very effective leader over the first 12 months of the project. For the pilots the methodology presented will be based a regular industrial business relation where the pilot-related members of the consortium will act as customers and the technological parties will act as a service provider.

b.	Has the collaboration between the beneficiaries been effective?

Comments

Although the consortium includes many parties the collaborations seems to be effective. Regular calls are made between the members of the team. All the parties seem to be involved. The technological partners are geographically based near the pilot partners, which makes it easier to get the pilot partners involved with the preparation of the project. Meetings held by the consortium are taking place in pilot sites in order to get them involved in the project. WP leaders (WPLs) have the responsibility to coordinate activities of their WP, define detailed time plans and delivery dates and to monitor execution from the various partners. In turn, each WP leader is supported by a number of Task Leaders (TLs), with similar role albeit at task level. In addition, for each pilot site, the consortium has appointed a Pilot Leader (PL), directly under the control of the Technical Manager who will be in charge of closely monitoring (and reporting on) the activities of the pilot once the pilot operational phase will start during the second year of activities. From an operational point of view, the project management team has enforced a set of actions to ensure smooth management of the activities such as conference calls on the various activities of the project; sharing of internal documents and emails among the consortium through i-locate project mailing lists. In addition, the PC has regular bi-monthly reports.

5.	POLICY SUPPORT and BROADER IMPACT

a.	Will the project have an impact on the implementation of the policies it supports?

Comments on the usefulness/sustainability/scalability/accessibility/usability of the results of the project (results can be for example services, content, specifications, reference implementations, source code, etc.).

The outcomes of the project will have a number of impacts. Specifically, with regard to the public portal, the mapping of thousands of venues will lead to great benefits. This will also create an impact at the EU level facilitating start-up of businesses based on indoor mapping data of publicly available spaces that will be facilitated as an open source i-locate toolkit. The consortium stated that recommendation towards supporting the policies is outside the scope of the project. The expert recommendations are that the consortium should contribute to solving regulatory issues which have been identified as a barrier by the consortium by providing a regulatory recommendations on European as well as the regions level. Finally, by providing an open platform for indoor GI, i-locate will make it possible for new companies to enter the market with innovative services based on indoor/outdoor localisation and tracking technologies. The public in the long run will be able to leverage the power of open GI for providing advanced services to businesses and citizens.

b.	Are the plans for the use and exploitation of results appropriate?

Comments on the plans of use of results of the consortium as a whole and for individual beneficiaries or groups, if applicable also outside of the consortium

The plans are appropriate. In the first year of i-locate, the partners have focused on raising awareness about the project among the general public and within relevant communities of potential customers (e.g. cities, hospitals, public bodies and large organisations, retailers, etc.), data providers, and technical developers (including SMEs). Liaisons have been established with several stakeholders targeted, including European projects, standardisation bodies, business and technical/industry market players. Those strategic partners have contributed to the definition of a long-term exploitation strategy for i-locate, their representatives have participated to workshops and events organised by the project, engaging into bilateral discussions with the partners and providing insights on the market relevance of outdoor/indoor location-based services and applications in a number of different sectors. The output of the pilots will allow for introduction of the new products to the market. It will also provide open-source software to create new business opportunities for third party companies. The additional recommendation of the experts are that the consortium could publish the assessment of different technologies used in different scenarios, comparison of the technologies and the best practises which would bring additional added value to the industry and strengthen the position of the consortium as the industry leader. Specific objectives for the first year are outlined in detail. All are reasonable.

c.	Have the beneficiaries disseminated project results and information adequately

Comments on dissemination and exploitation activities

A series of events targeted to the standardisation community, including presentation at OGC technical meeting and ETSI, have been complemented by actions towards the wider technical community with the organisation of 5 workshops under the i-locate flagship, and the participation to several other. Further action organised towards the technical community was the first i-locate challenge for the best project on indoor and outdoor LBS, which was awarded to Tudor research centre in Luxembourg. The project web-site and the i-locate LinkedIn group represented the two most used (and constantly updated) web channels which have gathered a significant attention by the specialised community, as demonstrated by its constant growth and the very active discussions engaged within the LinkedIn group by the broad expert community. The dissemination and awareness activities have also brought to significant attention from the press and media with 2 TV interviews, a very large number of press releases, and publications. Particularly worth mentioning is the special issue (August 2014) of the Geospatial World magazine, jointly edited with support of i-locate, which featured a number of articles by the partners of i-locate and the members of its advisory board. Visibility to the general public has also been ensured with the project being featured by popular science magazines as well as through the organisation of specific events opened to the public such as the “Internet of Places Days”, organised in the context of the Florence Youth & Heritage Festival in cooperation with NASA, ISOCARP (the international association of urban planners), and the Polytechnic of Milan. The first year was also marked by the first i-locate international conference, which took place in Florence in November 2014, and which featured a list of relevant speakers and which saw the participation of nearly 100 people.

d.	Are potential users and other stakeholders (also outside the consortium) suitably involved (if applicable)?

Comments

They have constructed a solid Advisory Board for the project. This involvement has been ensured through signature of a letter of intent. They have got seventeen experts so far from Europe, Asia, and USA. These are outlined briefly in the document. All seem relevant.

e.	Is the consortium interacting in a satisfactory manner with other related programmes projects or other relevant national/international programmes, standardisation bodies (if relevant)?

Comments

Yes, the project partners seem to have involved key stakeholders in the project. For instance, they have created strong ties with ILA (in-Location Alliance) who are the largest industrial grouping in the domain of indoor location based services (including large players such as NOKIA, Samsung, LG, Sony), which has expressed a strong interest in the results of i-locate and in particular in the business impact of a standardised platform for hybrid indoor/outdoor LBS. During the first reporting period, several meetings (in person and remotely) have been organised with top-management of ILA (including the Chair and Vice Chair) eventually bringing to the appointment of two members of the Advisory Board of the project. A specific meeting between several ILA members, OGC members, and i-locate was organised in fall 2014 in Rome at Telecom Italia to analyse in detail the details of the cooperation as well as a roadmap for engagement of ILA members in the activities of i-locate or for transfer of results of i-locate towards ILA members.

6.	OTHER ISSUES

a.	Have policy-related and/or regulatory issues been properly handled (if applicable)?

Comments

Yes. These are outlined in various sections of the report.

b.	Have ethical issues been appropriately handled (if applicable)?

Comments

Yes. These are outlined in various sections of the report.

c.	Have safety issues been properly handled (if applicable)?

Comments

Yes. These are outlined in various sections of the report.

Name (s) of the expert(s): Kevin Curran, Aleksander Buczkowski

Date:

Signature(s):

ANNEX I to the review report

Assessment of deliverables

| DELIVERABLES LIST STATUS |  |  |  |
| --- | --- | --- | --- |
| No. | Title | Status (Approve/Reject) | Comment |
| D1.1 | Use cases description and Privacy Threat Vulnerability and Risk Analysis | Approve |  |
| D1.2 | Regulatory constraints | Approve |  |
| D1.3 | Pilot scope description and system requirements | Approve |  |
| D1.4 | System Architecture | Approve |  |
| D2.1 | Data Survey Report | Approve |  |
| D2.2 | Analysis of open data repositories | Approve |  |
| D2.3 | Geospatial database with pilot-relevant data and open data connectors | Approve |  |
| D2.4 | Geometrical and Topological Model Checker | Approve |  |
| D3.1 | i-locate Toolkit v1.0 | Approve |  |
| D4.1 | Pilots deployment and validation plan | Approve |  |
| D6.1 | Fact Sheet | Approve |  |
| D6.2 | First version of the website and web 2.0 channels | Approve |  |
| D6.4 | First project media pack | Approve |  |
| D6.5 | First dissemination and exploitation report | Approve |  |
| D7.1 | Project charter | Approve |  |
| D7.2 | Risk log | Approve |  |

"The requirements of sound financial management, in particular regarding economy and efficiency refer to the standard of “good housekeeping” in spending public money. Economy can be understood as minimising the costs of resources used for an activity (input), having regard to the appropriate quality and can be linked to efficiency, which is the relationship between the outputs, in terms of resources used to produce them." Guide to Financial Issues, Article II.20(1).

In whole or in part or approval subject to certain conditions

Appropriate justification needs to be given

Comments are mandatory if deliverables are only accepted in part, or approval subject to certain conditions, or if they are rejected.  In case of suspected plagiarism, details should be given here and it should be mentioned under 2.c. of the report.